## Read Me
JMU ONLINE STUDENT REGISTRATION — RTM WORKBOOK
Purpose | Trace each FR/NFR to a story, acceptance criteria and test case.
Use | Filter the RTM by requirement, coverage status or test ID. Story IDs and AC IDs are working IDs; align them with the team's agreed convention before final filing.
Status meanings | Covered = all agreed ACs have tests; Partial = some test links exist but at least one scenario/test needs confirmation or adding; Gap / proposed = no approved test yet or proposed test IDs need reconciliation.
Important | TC-01 to TC-20 are listed as existing draft test cases. TC-21 to TC-37 are proposed in team drafts and must be reconciled with Group 3 before sign-off.
Source | Online Student Registration – Intern Problem Statement; Integration Specification Online Student Registration; TA4/TA3 working deliverables.

## RTM
Requirement ID | Type | Requirement summary | User story ID | Acceptance criteria ID(s) | Test case ID(s) | Coverage status | Gap / decision / notes
FR-01 | Functional | Register a student for an academic year and selected modules | US-FR-01 | AC-FR01-01; AC-FR01-02; AC-FR01-03 | TC-01; TC-10; TC-16; TC-17 | Partial | TC-01/10 cover basic success/duplicate; retry/parking links overlap NFR-02/NFR-03.
FR-02 | Functional | Retrieve a registration by reference number | US-FR-02 | AC-FR02-01; AC-FR02-02 | TC-02; add explicit not-found test | Partial | Confirm TC-02 covers both found and not-found outcomes.
FR-03 | Functional | Retrieve all registrations for a student | US-FR-03 | AC-FR03-01; AC-FR03-02; AC-FR03-03 | TC-03; add empty-list and unknown-student tests | Partial | Empty-list and unknown-student behaviour need confirmation and explicit tests.
FR-04 | Functional | Cancel before the cancellation deadline | US-FR-04 | AC-FR04-01; AC-FR04-02; AC-FR04-03 | TC-04; add deadline-passed and unauthorised-caller tests | Partial | Cancellation roles, deadline and failure status are open; current TC-04 expects 200/CANCELLED.
FR-05 | Functional | Validate student exists and is active | US-FR-05 | AC-FR05-01; AC-FR05-02 | TC-05; add inactive-student test | Partial | TC-05 covers unknown student; inactive response is not fully tested.
FR-06 | Functional | Check module eligibility and prerequisites | US-FR-06 | AC-FR06-01; AC-FR06-02; AC-FR06-03 | TC-07; TC-18; TC-19 | Partial | TC-18/19 cover SOAP fault/timeout; confirm retry policy and explicit success assertions.
FR-07 | Functional | Check for blocking fee debt | US-FR-07 | AC-FR07-01; AC-FR07-02 | TC-08; TC-01 (clear path assertion) | Partial | Ensure error code distinguishes fee block from OAuth scope denial.
FR-08 | Functional | Reject registrations over 160 credits per academic year | US-FR-08 | AC-FR08-01; AC-FR08-02 | TC-09; add exact-boundary test | Partial | Add a boundary test for exactly 160 credits.
FR-09 | Functional | Return a unique registration reference | US-FR-09 | AC-FR09-01; AC-FR09-02; AC-FR09-03 | TC-01; TC-16; TC-17 | Partial | Confirm reference generation before parking and duplicate prevention on replay.
FR-10 | Functional | Return consistent error responses: code, message, correlationId | US-FR-10 | AC-FR10-01; AC-FR10-02; AC-FR10-03 | TC-06; TC-20; add assertions to negative tests | Partial | TC-06 checks missing field; TC-20 checks correlation ID. Check standard fields across all errors.
NFR-01 | Non-functional | OAuth 2.0 on every API call; scopes per operation | NFR-S01 | AC-NFR01-01; AC-NFR01-02; AC-NFR01-03 | TC-11; TC-12; TC-13; add read-scope test | Partial | Current tests cover no token, invalid/expired token and missing write scope; read scope needs test.
NFR-02 | Non-functional | Retry database connection errors 3 times with 2/4/8 second backoff | NFR-S03 | AC-NFR02-01; AC-NFR02-02 | TC-15; proposed TC-26; add business-error-no-retry assertion | Partial | Reconcile proposed TC-26 with Group 3's test register.
NFR-03 | Non-functional | Park request on MQ after retries fail and return 202 with reference | NFR-S03 | AC-NFR03-01; AC-NFR03-02; AC-NFR03-03 | TC-16; TC-17; proposed TC-27–TC-30; add MQ-unavailable test | Partial | Reconcile proposed test IDs; confirm reference and replay/idempotency design.
NFR-04 | Non-functional | 95% of synchronous calls respond within 2 seconds | NFR-S07 | AC-NFR04-01; AC-NFR04-02 | Proposed TC-21 / TC-37; reconcile IDs | Gap / proposed | Performance test is proposed; agree load profile and treatment of retry-path calls.
NFR-05 | Non-functional | Limit each application to 100 calls per minute | NFR-S02 | AC-NFR05-01; AC-NFR05-02 | TC-14; add positive within-limit test | Partial | TC-14 covers over-limit response; add a within-limit assertion.
NFR-06 | Non-functional | Log correlationId at APIC and ACE for every request | NFR-S04 | AC-NFR06-01; AC-NFR06-02 | TC-20; proposed TC-31–TC-32 | Partial | Reconcile proposed IDs and verify propagation, response and both logs.
NFR-07 | Non-functional | Do not log ID numbers or personal data | NFR-S05 | AC-NFR07-01; AC-NFR07-02 | Proposed TC-22; proposed TC-33–TC-34 | Gap / proposed | Privacy/logging test and student-number treatment need confirmation; reconcile test IDs.

## Story Index
Story ID | Linked requirement(s) | Story title | Acceptance criteria IDs | Build / API reference
US-FR-01 | FR-01 | Register a student | AC-FR01-01; AC-FR01-02; AC-FR01-03 | POST /registrations
US-FR-02 | FR-02 | Retrieve registration by reference | AC-FR02-01; AC-FR02-02 | GET /registrations/{ref}
US-FR-03 | FR-03 | Retrieve registrations for a student | AC-FR03-01; AC-FR03-02; AC-FR03-03 | GET /students/{studentNumber}/registrations
US-FR-04 | FR-04 | Cancel a registration | AC-FR04-01; AC-FR04-02; AC-FR04-03 | DELETE /registrations/{ref}
US-FR-05 | FR-05 | Validate student exists and is active | AC-FR05-01; AC-FR05-02 | Student Database lookup in ACE
US-FR-06 | FR-06 | Check module eligibility | AC-FR06-01; AC-FR06-02; AC-FR06-03 | ACE calls Academic Records SOAP mock (CheckEligibility)
US-FR-07 | FR-07 | Check blocking fee debt | AC-FR07-01; AC-FR07-02 | ACE calls Finance SOAP mock (CheckFeeStatus)
US-FR-08 | FR-08 | Enforce annual credit limit | AC-FR08-01; AC-FR08-02 | Business rule in ACE using module credit values
US-FR-09 | FR-09 | Return a unique reference | AC-FR09-01; AC-FR09-02; AC-FR09-03 | POST /registrations response and parked-message metadata
US-FR-10 | FR-10 | Return a consistent error response | AC-FR10-01; AC-FR10-02; AC-FR10-03 | Shared APIC/ACE error mapping across API operations
NFR-S01 | NFR-01 | Enforce OAuth 2.0 authentication and scopes | AC-NFR01-01; AC-NFR01-02; AC-NFR01-03 | API Connect OAuth 2.0 provider and API policies
NFR-S02 | NFR-05 | Limit API request rate | AC-NFR05-01; AC-NFR05-02 | API Connect product/plan rate-limit policy
NFR-S03 | NFR-02 / NFR-03 | Recover from database outages without losing registrations | AC-NFR02-01; AC-NFR02-02; AC-NFR03-01; AC-NFR03-02; AC-NFR03-03 | ACE retry logic; REG.PARKED.Q; REG.BACKOUT.Q
NFR-S07 | NFR-04 | Meet the synchronous response-time target | AC-NFR04-01; AC-NFR04-02 | Performance test against APIC/ACE and healthy backends
NFR-S04 | NFR-06 | Trace requests using correlation IDs | AC-NFR06-01; AC-NFR06-02 | APIC policy and shared ACE logging/error handling
NFR-S05 | NFR-07 | Protect personal data in logs | AC-NFR07-01; AC-NFR07-02 | APIC/ACE logging and masking

## Test Case Register
Test case ID | Scenario | Expected result / assertion | Linked requirement(s) | Status / notes
TC-01 | Successful registration | 201 Created; reference returned | FR-01; FR-09 | Existing in draft
TC-02 | Retrieve registration by reference | 200 OK; correct details | FR-02 | Existing in draft; add explicit 404 case if not already covered
TC-03 | Retrieve registrations for a student | 200 OK; list returned | FR-03 | Existing in draft
TC-04 | Cancel before deadline | 200 OK; status CANCELLED (current draft) | FR-04 | Existing in draft; confirm 200 vs 204
TC-05 | Unknown student | 404; standard error; no retry | FR-05 | Existing in draft
TC-06 | Missing mandatory field | 400; standard error fields | FR-10 | Existing in draft
TC-07 | Module eligibility / prerequisite validation | Reject NOT_ELIGIBLE with agreed response | FR-06 | Existing in draft
TC-08 | Blocking fee debt | Reject with FEE_BLOCKED; draft proposes 403 | FR-07 | Existing in draft
TC-09 | Registration exceeds 160 credits | Reject with agreed credit-limit response | FR-08 | Existing in draft
TC-10 | Duplicate registration for same student/year | 409 Conflict | FR-01; BR-02 | Existing in draft
TC-11 | No OAuth token | 401 Unauthorized | NFR-01 | Existing in draft
TC-12 | Invalid / expired token | 401 Unauthorized | NFR-01 | Existing in draft; confirm cases represented
TC-13 | Token without registration.write scope calls POST | 403 Forbidden | NFR-01 | Existing in draft
TC-14 | More than 100 calls/minute | 429 Too Many Requests | NFR-05 | Existing in draft
TC-15 | Database connection failure; retry behaviour | Retry with configured 2/4/8-second backoff; recover if DB returns | NFR-02 | Existing in draft; verify exact retry count and timing
TC-16 | Retries exhausted; request parked | 202 Accepted; reference; PENDING; message on REG.PARKED.Q | NFR-02; NFR-03; FR-09 | Existing in draft
TC-17 | Queued request processed after DB recovery | Saved once; same reference; CONFIRMED | NFR-03; FR-09 | Existing in draft; add duplicate replay assertion
TC-18 | Academic Records SOAP fault | 502 with standard error model (draft) | FR-06; FR-10 | Existing in draft
TC-19 | Academic Records mock delays 10 seconds | 504 with standard error model (draft) | FR-06; FR-10 | Existing in draft
TC-20 | CorrelationId in response and logs | Same value in response, APIC logs and ACE logs | FR-10; NFR-06 | Existing in draft
TC-21 (proposed) | Performance under realistic load | At least 95% of synchronous calls within 2 seconds | NFR-04 | Proposed; conflicts with TA3's proposed numbering—reconcile
TC-22 (proposed) | Inspect logs for personal data | No ID numbers or personal data in APIC/ACE logs | NFR-07 | Proposed in integration spec; reconcile with TC-33/34
TC-23 (proposed) | Additional OAuth/scope negative case | Agreed 401/403 behaviour for relevant token/scope case | NFR-01 | Proposed; exact scenario must be defined
TC-24 (proposed) | Rate limit remains available within limit | Requests within 100/minute are not blocked by rate limit | NFR-05 | Proposed
TC-25 (proposed) | Rate-limit window/application isolation | Limit is applied per application per minute | NFR-05 | Proposed
TC-26 (proposed) | Retry count and backoff verification | 3 retries with waits 2, 4, 8 seconds for DB connection errors | NFR-02 | Proposed; reconcile IDs
TC-27 (proposed) | Parked message contains original request and metadata | Request, reference and correlationId stored on REG.PARKED.Q | NFR-03; FR-09 | Proposed
TC-28 (proposed) | 202 response for parked request | 202 with reference and PENDING | NFR-03; FR-09 | Proposed
TC-29 (proposed) | MQ put failure | 503 and fatal failure logged if request cannot be parked | NFR-03 | Proposed from integration specification
TC-30 (proposed) | Replay after DB recovery | Registration confirmed using same reference | NFR-03; FR-09 | Proposed; reconcile IDs
TC-31 (proposed) | CorrelationId generated if missing | APIC supplies correlationId and propagates to ACE | NFR-06 | Proposed
TC-32 (proposed) | CorrelationId preserved through flow | Same correlationId in APIC/ACE logs and response | NFR-06; FR-10 | Proposed
TC-33 (proposed) | Sensitive data excluded from logs | No ID numbers or personal data in logs | NFR-07 | Proposed; reconcile with TC-22
TC-34 (proposed) | Student number masked or omitted in logs | Student number masked/omitted under agreed policy | NFR-07 | Proposed
TC-35 (proposed) | Academic Records SOAP fault error handling | Agreed 502 response and standard error structure | FR-06; FR-10 | Proposed; TA3 link to NFR-02/NFR-04 requires confirmation
TC-36 (proposed) | Academic Records timeout error handling | Agreed 504 response and standard error structure | FR-06; FR-10 | Proposed; TA3 link to NFR-02/NFR-04 requires confirmation
TC-37 (proposed) | Synchronous response time | 95% of calls within 2 seconds under agreed test conditions | NFR-04 | Proposed; reconcile with TC-21